## Open Issues from DQA
[6 empty] | Daily Quality Audit Follow Up List |  |  |  | http://pmdadashboard/d/DluY5Ph4z/daily-shift-quality-audit-report?orgId=1&var-QA_ReportNo=All&from=now%2Fy&to=now%2Fy
Date | Shift | Report Number | Section | Quality Technician | Category | Description | Action Taken | Follow Up Comments | Follow Up Person | Respnsible | Completed? | Target Completion Date | Date completed
02-05-2023 | Afternoon | QAR00043 | Specific Requests | Abdul K. | Nonconforming Material | 58.9903.9658 | NCR 804 coinnd parts | Need to review parts and report for futher disposition | Virginia.A | Virginia Avery | N | 2023-05-29
06-05-2023 | Afternoon | QAR00048 | Specific Requests | Abdul K. | Other | X22 Body - Dim 27 split pin to A - coining | Technician tried 3 core rods and none are making a difference Looked up compacting data and last days worth of compacted parts were run high Comparing tonnage and part height to that of the firstoff to determine what adjustments we can make. Admittantly reluctant to write a RID when the last one was rejected by QE, also most recent adjustments would not have met RID spec. As per VVT supervisor press is down until parts can meet spec. | Please review data and evaluate | Tom | Tom Condello | N | 2023-05-31

## Closed Issues from DQA
[6 empty] | Daily Quality Audit Follow Up List |  |  |  | http://pmdadashboard/d/DluY5Ph4z/daily-shift-quality-audit-report?orgId=1&var-QA_ReportNo=All&from=now%2Fy&to=now%2Fy
Date | Shift | Report Number | Section | Quality Technician | Category | Description | Action Taken | Follow Up Comments | Follow Up Person | Respnsible | Completed? | Target Completion Date | Date completed
27-04-2023 | Day | QAR00036 | Specific Requests | Gary M. | Communication Record | Communication ZF Body | Signed off Days shift EPC, Added cert sheet to 2 skids in shipping | continue sign offs | Sooraj, Abdul | Quality Technicians | N |  | 2023-04-27
28-04-2023 | Night | QAR00037 | Specific Requests | Abdul K. | Communication Record | CR&R and communications records for ZF body and 10R80 rptor | Communicated in night shift | keep communicate in other shifts | Q.Tech | Quality Technicians | N |  | 2023-04-28
01-05-2023 | Afternoon | QAR00041 | Specific Requests | Abdul K. | Internal Deviation | RID | Issued RID 23-0160 | To provide more probes | Geoff.B | Geoff Boyer | N |  | 2023-05-01
02-05-2023 | Night | QAR00042 | Specific Requests | Gary M. | Communication Record | Communication record | Communicated change in process control sheets to grinding operators and team leads on shift. | continue to sign off operators | QTs | Quality Technicians | N |  | 2023-05-02
02-05-2023 | Afternoon | QAR00043 | Specific Requests | Abdul K. | Nonconforming Material | 58.9903.9658 | NCR 804 coinnd parts | Need to review parts and report for futher disposition | Virginia.A | Virginia Avery | N |  | 2023-05-02
03-05-2023 | Night | QAR00044 | Specific Requests | Gary M. | Internal Deviation | Tour 9200 line (10R140 rotor calibration) | Wrote RID 23-0163 for induction hardnening metlab report as the screen at induction does not have a reading for total quench used. Observed TPMs being completed, in process checks being done and stressed the importance of completeing I charts and not having unidentified parts laying around See 6210 bypass check below | Follow up on Metlab RID 23-0163 | Fraser, Ken | Ken Servos | N |  | 2023-05-03
03-05-2023 | Afternoon | QAR00045 | Specific Requests | Abdul K. | Internal Deviation | Rid | Issued Rid23-0167 | root cause analysis | Ken.S | Ken Servos | N |  | 2023-05-03
06-05-2023 | Afternoon | QAR00048 | Specific Requests | Abdul K. | Other | X22 Body - Dim 27 split pin to A - coining | Technician tried 3 core rods and none are making a difference Looked up compacting data and last days worth of compacted parts were run high Comparing tonnage and part height to that of the firstoff to determine what adjustments we can make. Admittantly reluctant to write a RID when the last one was rejected by QE, also most recent adjustments would not have met RID spec. As per VVT supervisor press is down until parts can meet spec. | Please review data and evaluate | Tom | Tom Condello | N |  | 2023-05-06
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Internal Deviation | RID - 2200 Die heater | Issued RID 23-0182 Die Heater Ref Only | please review escalation and adjust if needed | Virginia | Virginia Avery | N |  | 2023-05-11
11-05-2023 | Afternoon | QAR00049 | Critical Calls | Gary M. | Nonconforming Material | Crack check - Snowtiger slides | Contained 2328pcs under NCR 48044 Adjustment was made, Supervisor made the decision to error on the side of caution and run positive recall only into racks (opposed to furnace) | Paul reviewed micro but due to high number of parts and possible breakpoint within the cage Hold for QM | Paul, Mike | Mike Eechauate | N |  | 2023-05-11
11-05-2023 | Afternoon | QAR00049 | Critical Calls | Gary M. | Nonconforming Material | 10R80 Body - Uncoined section by kidney hole | Contained parts under NCR 48048 and 48047 | Please review and evaluate potential for re-coin | Tom | Tom Condello | N |  | 2023-05-11
11-05-2023 | Afternoon | QAR00049 | Critical Calls | Gary M. | Nonconforming Material | 58.7406.7406 - containment due to coining mark | Contained parts under NCR 48045 and 48046 as per PM, surface finish data collected and placed on Kens desk | Review and evaluate data | Ken, Paul | Ken Servos | N |  | 2023-05-11
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Communication Record | Communication record - Gear NDT retain rejects for QE review | Signed off operators | Please continue to sign off operators on each shift | Sooraj, Abdul | Quality Technicians | N |  | 2023-05-11
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Nonconforming Material | 10R80 rotors sinter 3300 low dim 17 counterbore | Contained under NCR 48049 | Please review and disposition | Tom | Tom Condello | N |  | 2023-05-11
12-05-2023 | Day | QAR00051 | Bypass List | Abdul K. |  | Bore Gauge Slot Gauge, Vision, Eddy Current - 10R80 Rotor - 82.0008.2928 | Bore checker disable does no evalate counter bore ,so 100 % off line inspection | Waiting for sensor | Elsie.A |  | N |  | 2023-05-12
12-05-2023 | Day | QAR00051 | Specific Requests | Abdul K. |  | 58.0406.3406 | NCR 1061 sinter parts | 100 % sort off line with snap gauge -12 (4.600 -4.800 mm) | Q.Tech |  | N |  | 2023-05-12
12-05-2023 | Afternoon | QAR00052 | Specific Requests | Abdul K. |  | 58.7680.7680 - oversize after coin | Placed cage on hold from coining dispositioned to be recoined for oversized condition | recoin | ken |  | N |  | 2023-05-12
12-05-2023 | Afternoon | QAR00052 | Critical Calls | Abdul K. |  | 58.7406.7406 - Additional damage found on parts contained last night, damage goes beyond these two cages | Examined the WIP cages and determined that the damage was not contained to punch mark damaged cages. Contained 6 additional cages all found to have the same damage. Source | create boundary samples | Ken |  | N |  | 2023-05-12
13-05-2023 | Day | QAR00054 | Bypass List | Gary M. |  | Slot Gauge Vision, Eddy Current - 10R80 Rotor - 82.0008.2928 | Ongoing issue with Dial Table install | RID 23-0164 100% slot inspection with semi auto cell, 200% Visually inspection for Chipping and Cracks | Tom |  | N |  | 2023-05-13
13-05-2023 | Day | QAR00054 | Specific Requests | Gary M. |  | Snow tiger slides - CMM and PCS do not match | Verified that PCS is the correct revision, with no other information PCS is followed - no need to contain | Please update cmm and/or confirm pcs is accurate | Parth, Tom |  | N |  | 2023-05-13
13-05-2023 | Day | QAR00054 | Specific Requests | Gary M. |  | Training - scale calibration | Worked with Majaz and learned how to properly calibrate the scale | evaluate 238 Monday morning and close RID | Majaz, Gary |  | N |  | 2023-05-13
15-05-2023 | Night | QAR00055 | Bypass List | Abdul K. |  | Bore Gauge Slot Gauge, Vision, Eddy Current - 10R80 Rotor - 82.0008.2928 | Bore checker disable,RID in | Waiting for parts | Elsie.A |  | N |  | 2023-05-15
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. |  | Comunication for QA-000815 | Communicate in night shift | Need to communicate all shift | Q.Tech |  | N |  | 2023-05-15
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. |  | Communication record | Communicate in night shit | Communicate in all shift | Q.Tech |  | N |  | 2023-05-15
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. |  | communication record | Communicate in night shift | communicate in all shift when complete hand over to Spencer.F | Q.Tech |  | N |  | 2023-05-15
15-05-2023 | Night | QAR00055 | Critical Calls | Abdul K. |  | 35.1840.4941 | Checked PCS(F/O,in process) this check not required | Need to update about this check | Paul.M |  | N |  | 2023-05-15
15-05-2023 | Day | QAR00056 | Bypass List | Gary M. |  | Slot Gauge Vision, Eddy Current - 10R80 Rotor - 82.0008.2928 | continued issues with table repair/ install | RID 23-0164 allows for manual inspection with table install is being completed | Tom |  | N |  | 2023-05-15
15-05-2023 | Day | QAR00056 | Specific Requests | Gary M. |  | 1008 bad steam quality | Reviewed by PM, no containment required investigate steam flow parameters with Jeff L. | Gary, Paul | Follow up with Jeff L. Re steam parameters tolerances. |  | N |  | 2023-05-15
15-05-2023 | Night | QAR00056 | Bypass List | Abdul K. |  | Bore Gauge Slot Gauge, Vision, Eddy Current - 10R80 Rotor - 82.0008.2928 | Bore checker disable does not evaluate countrbore so manual 100% offline inspection,see app I-1785 | waiting for parts | Elsie Alonso |  | N |  | 2023-05-15
16-05-2023 | Afternoon | QAR00058 | Specific Requests | Sooraj K. | Other | 1956 CP - 3500 furnace | Parts re-sintered and held for evaluation | evaluate re-sinter parts for hardness | Fraser Baguma, Gary Martin | Quality Technicians | Y |  | 2023-05-26
17-05-2023 | Night | QAR00059 | Specific Requests | Abdul K. | Nonconforming Material | 70.3161.3161(snow tiger slide) | Issued NCR | 100 % check in SG -10 off line | Gary Martin |  | Y |  | 2023-05-26
17-05-2023 | Day | QAR00060 | Critical Calls | Gary M. | Other | Snow tiger slides - containment | Coining mark on oil port, NCRd cages as per TC, cage with breakpoint was dispositioned as Sort for Breakpoint | Tom please review | Thomas Condello | Tom Condello | Y |  | 2023-05-26
17-05-2023 | Day | QAR00060 | Specific Requests | Gary M. | Other | 1956 hardness / powder issue | Working with Virginia to determine the scope of the containment needed | Need to determine scope of containment | Virginia Avery | Virginia Avery | Y |  | 26-May,23
25-05-2023 | Day | QAR00077 | Critical Calls | Sooraj K. | Gauging | DV 6.2 slide - Verifying gauge | Troubleshot and worked with Majaz | Majaz resolving the gauge . | Majaz Ali |  | Y |  | 2023-05-26
11-05-2023 | Afternoon | QAR00049 | Critical Calls | Gary M. | Nonconforming Material | 10R80 Body - Uncoined section by kidney hole | Contained parts under NCR 48048 and 48047 | Please review and evaluate potential for re-coin | Tom | Tom Condello | Y | 2023-05-29 | 2023-05-26
11-05-2023 | Afternoon | QAR00049 | Critical Calls | Gary M. | Nonconforming Material | 58.7406.7406 - containment due to coining mark | Contained parts under NCR 48045 and 48046 as per PM, surface finish data collected and placed on Kens desk | Review and evaluate data | Ken, Paul | Ken Servos | Y | 2023-05-29 | 2023-05-26
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Nonconforming Material | 10R80 rotors sinter 3300 low dim 17 counterbore | Contained under NCR 48049 | Please review and disposition | Tom | Tom Condello | Y | 2023-05-29 | 2023-05-26
01-05-2023 | Afternoon | QAR00041 | Specific Requests | Abdul K. | Internal Deviation | RID | Issued RID 23-0160 | To provide more probes | Geoff.B | Geoff Boyer | N | 2023-05-31 | 2023-05-26
03-05-2023 | Night | QAR00044 | Specific Requests | Gary M. | Internal Deviation | Tour 9200 line (10R140 rotor calibration) | Wrote RID 23-0163 for induction hardnening metlab report as the screen at induction does not have a reading for total quench used. Observed TPMs being completed, in process checks being done and stressed the importance of completeing I charts and not having unidentified parts laying around See 6210 bypass check below | Follow up on Metlab RID 23-0163 | Fraser, Ken | Ken Servos | N | 2023-05-31 | 2023-05-29
03-05-2023 | Afternoon | QAR00045 | Specific Requests | Abdul K. | Internal Deviation | Rid | Issued Rid23-0167 | root cause analysis | Ken.S | Ken Servos | N | 2023-05-31 | 2023-05-29
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Internal Deviation | RID - 2200 Die heater | Issued RID 23-0182 Die Heater Ref Only | please review escalation and adjust if needed | Virginia | Virginia Avery | N | 2023-05-31 | 2023-05-26
17-05-2023 | Night | QAR00059 | Specific Requests | Abdul K. | Internal Deviation | Steamer Validation | Checked parts in Met lab for steam quality and CMM for dimensns all check OK,issued Rid 23-0187 | Need to update steamer load matrix | Kelly.K | Quality Technicians | N | 2023-05-31 | 2023-05-26
27-04-2023 | Day | QAR00036 | Specific Requests | Gary M. | Communication Record | Communication ZF Body | Signed off Days shift EPC, Added cert sheet to 2 skids in shipping | continue sign offs | Sooraj, Abdul | Quality Technicians | Y | 2023-04-30 | 2023-05-29
02-05-2023 | Night | QAR00042 | Specific Requests | Gary M. | Communication Record | Communication record | Communicated change in process control sheets to grinding operators and team leads on shift. | continue to sign off operators | QTs | Quality Technicians | Y | 2023-05-05 | 2023-05-29
28-04-2023 | Night | QAR00037 | Specific Requests | Abdul K. | Communication Record | CR&R and communications records for ZF body and 10R80 rptor | Communicated in night shift | keep communicate in other shifts | Q.Tech | Quality Technicians | Y | 2023-05-01 | 2023-05-29
11-05-2023 | Afternoon | QAR00049 | Specific Requests | Gary M. | Communication Record | Communication record - Gear NDT retain rejects for QE review | Signed off operators | Please continue to sign off operators on each shift | Sooraj, Abdul | Quality Technicians | Y | 2023-05-14 | 2023-05-29
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. | Communication Record | Comunication for QA-000815 | Communicate in night shift | Need to communicate all shift | Q.Tech | Quality Technicians | Y | 2023-05-18 | 2023-05-29
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. | Communication Record | Communication record | Communicate in night shit | Communicate in all shift | Q.Tech | Quality Technicians | Y | 2023-05-18 | 2023-05-29
15-05-2023 | Night | QAR00055 | Specific Requests | Abdul K. | Communication Record | communication record | Communicate in night shift | communicate in all shift when complete hand over to Spencer.F | Q.Tech | Quality Technicians | Y | 2023-05-19 | 2023-05-29
19-05-2023 | Night | QAR00063 | Specific Requests | Abdul K. | Communication Record | 58.0406.3406 and 58.0404.4406 | Until further notice ,each skid must have aFord Supplier Quality Alert posted a4 side pf the skid | Need tocommunicate all shifts | Quality Technician | Quality Technicians | Y | 2023-05-23 | 2023-05-29
19-05-2023 | Night | QAR00063 | Specific Requests | Abdul K. | Communication Record | 58.9933.9929 an 58.9933.9930 | Issued Communication | comuniate all shifts | Quality Technician | Quality Technicians | Y | 2023-05-23 | 2023-05-29
23-05-2023 | Day | QAR00071 | Specific Requests | Abdul K. | Communication Record | 82.0146.0146 | Issued communication ecod with QA-00820 | Need to communicate all shifts | Quality Technician | Quality Technicians | Y | 2023-05-29 | 2023-05-29
23-05-2023 | Afternoon | QAR00072 | Specific Requests | Abdul K. | Communication Record | 70.2899.2899(Nano slide) | Issued Communicaton record with QA-00818 | Communicate in all shifts | Quality Technician | Quality Technicians | Y | 2023-05-29 | 2023-05-29
23-05-2023 | Afternoon | QAR00072 | Specific Requests | Abdul K. | Communication Record | 82.4679.7277(10R80 body) | Issued communication record with QA-00819 | Communicate in all shits | Quality Technician | Quality Technicians | Y | 2023-05-29 | 2023-05-29
26-05-2023 | Afternoon | QAR00081 | Specific Requests | Abdul K. | Internal Deviation | 6170 NDT | Issued RiD 23-0202 | Need to update RI | Elsie Alonso | Quality Technicians | N | 2023-05-29 | 2023-05-29
26-05-2023 | Night | QAR00079 | Critical Calls | Gary M. | Nonconforming Material | Helical gear bottom rim relief step oversize | contained under NCR 48100, 48099 | Review and disposition | Spencer Fullerton | Spencer | N | 2023-05-29 | 2023-05-29
26-05-2023 | Afternoon | QAR00081 | Specific Requests | Abdul K. | Nonconforming Material | 82.0194.0194(10R140 Slide) | NCR parts with disposition Check filters /rewash and submit parts in Met lab for sediment | Need to releae parts ,if sediment test pass in Met lab | Quality Technician | Quality Technicians | N | 2023-05-29 | 2023-05-29
27-05-2023 | Night | QAR00082 | Critical Calls | Gary M. | Nonconforming Material | 10R80 Body - compacting concern | Tech put 3 parts in to cmm at suspect point (no cmm operator on nights), contained parts at that point and after. Visually inspected previous cage and see no visable signs of crack, with no diserarnable breakpoint as crackchecks don't get done in process Parts get 100% ping tested at sinter unload and then again at steam unload, any failing parts get scrapped. - NCR 48105 | Disposition after metlab results | Thomas Condello | Thomas Condello | N | 2023-06-01 | 2023-05-29